## Summary
MSDI Data Improvement Plan
Theme: Cadastral Framework Steward: Jeff Hedstrom, Montana State Library
Subthemes: Cadastral National Spatial Data Infrastructure (CadNSDI), Owner Parcels, Public Lands, and Conservation Easements
Summary
Long-term Goals: (In no particular order)
1) All missing data incorporated into the CadNSDI dataset
2) Acquire 35% of the control for every "surveyed" township corner of the state and make adjustments to those coordinates (10 year goal)
3) Additional resources are made available to help users work with SQL databases more efficiently, reducing the learning curve
4) Improvements made to routing process to ensure new Conservation Easements are entered into the GIS data in a more timely manner
5) Public Lands dataset contains significantly less unintended gaps / overlaps (goal to have 75% of identified errors fixed)
Near-term Goals: (In no particular order)
1) Develop an evaluation metric to assist with identifying areas of need of adjustment/additional control
2) Availability of data in more formats on-demand and/or the ability to apply desired filters (ArcGIS Hub of the MSDI data)
3) Investigate how to make improvements to the Orion Data Service to ensure it returns the correct property information
4) Publish parcels semi-monthly (combat large number of county split/combos)
5) Complete metadata for all datasets
6) Incorporate missing GLO surveys into the CadNSDI dataset
7) Implement topology checks to detect overlaps and gaps on the public lands dataset
8) Develop a better mechanism to detect ownership changes that impact public lands
9) Work with providers to ensure the integrity needs of a seamless, statewide dataset are met (Ownerparcels)

## Data Improvement Plan
MSDI Data Improvement Plan
Theme: Cadastral Framework
Data Theme | Measure | Outcome | Action | Ongoing Action (Y/N) | Progress Assessment (Date) | LOE (staff time) | LOE/Cost External Support | Infrastructure Cost | Feasibility and Comments
Theme/ Sub-theme or Dataset | select from list | <Describe desired outcome, headed by time frame: “Current”; “Near-term”; “Long-term”> | <Actions needed to achieve outcome> | <Is the action underway (Y/N); may note reoccuring> | <Date and progress toward outcome; may be updated> | <Can the action be accomplished at current staffing (y/n)? Provide an estimate of hours> | <Is external support needed (y/n)? Provide an estimate of hours or cost> | <Is the necessary infrastructure in place (y/n). Provide an estimate of cost.> | <Note that future ideas, currently infeasible, can be listed>
Owner Parcels | Update Frequency | Current: Publish monthly | In place | Y, reoccuring |  | Y (100 hours / year) |  |  | The current QAQC process takes "some" manual work and half of the day to process
Owner Parcels | Update Frequency | Near-term: Publish semi-monthly | Streamlining QAQC process, coordination with providers and semi-monthly task schedule data publishing routines | N, reoccuring |  | Y (175 hours / year) |  |  | This task "could" be possible given the current workflow if more of the busier counties got more frequent updates. We will know more once we are in ROK if managed services can be updated more than once a month.
Owner Parcels | Update Frequency | Long-term: Publish weekly | Streamlining QAQC process, coordination with providers and weekly task schedule data publishing routines | N, reoccuring |  | N (800 hours / year) |  |  | The QAQC workflow would need to be cutback as we do not have the staff to update parcels on a weekly basis given the cadastral framework workload
Owner Parcels | Update Frequency | Long-term: Publish near real-time | Streamlining QAQC process, coordination with providers and daily task schedule data publishing routines | N, reoccuring |  | N (??) |  | New server? $10,000 | The entire QAQC workflow would be eliminated, making coordination with parcel providers more important, a daily or change parcel update would equate to a more thoroughly parcel QC on a daily or more frequent basis.
Owner Parcels | Archive Frequency | Current: Monthly archives, yearly snapshots made publicly available | In place | Y, reoccurring |  | Y
Owner Parcels | Archive Frequency | Near-term: Semi-monthly archives, make a semi-annual snapshot pubicly available | Automating this process to occur every "x" day of the month | N, reoccurring |  | Y |  |  | Making multiple versions a month available to public would be a large leap given we don't even make our monthly archives available
|  | Near-term: Make historic snapshots available in nearly in any format | Develop Open Data Site | N | 50% - 5/13/2026 | Y
Owner Parcels | Archive Frequency | Long-term: Archive every version of the db, make available to the public | Unknown how this might be possible since multiple agencies maintain this dataset and the coordination effort would be substatial | N | 0% | N |  | New server? $10,000
Owner Parcels | Precision/Accuracy | Current: Varies across state (+/- 160 meters to +/- 0.1 meter) | In place | Y
Owner Parcels | Precision/Accuracy | Near-term: Adjust areas identifed that are most in need of adjustment (survey control or re-COGO) with available funding and resources | Identify areas in-need the most of an adjustment by creating a map that is updated annually and clearly shows the "need" areas | N, reoccurring
Owner Parcels | Precision/Accuracy | Long-term: Adjust areas identifed that are most in need of adjustment (survey control or re-COGO) and available funding and resources has been prioritized to adjust these areas | Continue to adjust areas "in-need" the most and prioritize any funding and resources accordingly | N, reoccurring |  | Y
Owner Parcels | Consistency | Current: Adjust parcel geometry to the latest CadNSDI | In place | Y, reoccurring based on publication |  | Y (40 hours) |  |  | Additional time is typically added due to coordination with DOR and working around their GIS Analysts' schedules
Owner Parcels | Consistency | Current: Not all independent counties share their parcels data using the state standard coordinate system | In place | Y
Owner Parcels | Consistency | Current: Property Address not always correct with the offical address for the property | In place | Y
Owner Parcels | Consistency | Near-term: Work with all providers to share their parcel data using the state standard coordinate system | Coorindate with all parcel providers | Y | 20% - 4/21/2026 | Y (unknown)
Owner Parcels | Consistency | Near-term: Work with the Structures Theme Stewards and DOR to QA/QC Property Addresses with official addresses | Coordination with DOR | N | 0% | Y
Owner Parcels | Consistency | Long-term: DOR verifies Property Address with official address points prior to entry and validates addresses on a set schedule | Coordination with DOR | N | 0% | Y
Owner Parcels | Completeness | Current: Statewide coverage, on-going maintenance | In place | Y, reoccurring |  |  |  |  | Data providers (DOR & Independent Counties) maintain the OwnerParcels geometry
Owner Parcels | Completeness | Current: CAMA is missing data for some federal/state owned areas | In place | Y
Owner Parcels | Completeness | Near-term: Investigate how to delineate a mass number of CAMA attribution and import them into the Orion data | Coordination with DOR | N | 0% | Y |  |  | DOR doesn't priority exempt property changes, this objective could be different if a systematic apporach could be discovered. We have had talked with DOR about it, something could happen as a long-term objective
Owner Parcels | Completeness | Long-term: All parcels have a minimum set of CAMA attributes populated | Coordination with DOR | N | 0% | Y
Owner Parcels | Timeliness | Current: Parcel geometry is updated on a monthly basis, with about a 10 day lag between when the ftp is update and the web service that updates the Cadastral App | In place | Y, reoccurring
Owner Parcels | Timeliness | Current: Orion Data Service is refreshed with updated data on a nightly basis | In place | Y, reoccurring
Owner Parcels | Timeliness | Current: Newly filed surveys between the months January and June do not get inputted into the parcel data geometry until post July, meaning there can be up to an 8 month time lapses between when the data is refreshed | In place | Y
Owner Parcels | Timeliness | Near-term: Improve the lag between when the ftp parcels are updated and the web services | Communication with Managed Services team | N | 0% | Y |  |  | MSL is migrating its' services and data to the cloud, ROK will be taking over the managed services and this will likely be a priority to improve the data update lag
Owner Parcels | Integrity | Current: Parcels are not seamless at the county boundary line, 2) Parcel attribute validation concerns statewide | In place | Y, reoccurring
Owner Parcels | Integrity | Current: Parcel-CAMA relational issues, does not return the correct property information in rare cases | In place | Y
Owner Parcels | Integrity | Near-term: Work with providers to ensure the integrity needs of a seamless, statewide dataset are met | Coordination with all parcel providers | N | 0% | Y | DOR/Int. Counties would need to be onboard with implementing |  | This objective needs all parcel providers need to be onboard to work towards a common, seamless goal
Owner Parcels | Integrity | Near-term: Implement a CAMA attribution validation mechanism / process | Coordination with all parcel providers | N | 0% | Y | DOR/Int. Counties would need to be onboard with implementing |  | This objective entails implementing a validation system to compare the entered the parcel geocode with the CAMA and it properly validates in the geographic position
Owner Parcels | Integrity | Near-term: Investigate how to make improvements to the Orion Data Service to ensure it returns the correct property information | Coorindation with MSL Application Development team and DOR | N | 0% | N (unknown) | Y (Additional funding is needed for improvements to be made to the Orion Data Service) | Unknown | Improvements to the Orion Data Service is a large task that needs funding. These other two objectives involves coordinate with data providers
Owner Parcels | Integrity | Long-term: 1) Parcels are seamless between each county and regular QC is performed, 2) CAMA attribution pass minimum validations | Coordination with all parcel providers | N | 0% | Y
Owner Parcels | Integrity | Long-term: The Orion Data Service and prarcel relational database working more effectively | Coorindation with MSL Application Development team and DOR | N | 0% | N (unknown) | Y (Additional funding is needed for improvements to be made to the Orion Data Service) | Unknown | This goal will take external support, it is unknown what the full cost will be, one is fair to estimate that tweaking of the current data service will be required in order to accomplish this goal
Owner Parcels | Relevance | Current: Datasets are available to partners and the public in several formats | In place | Y
Owner Parcels | Relevance | Current: SQL databases are availavle on the ftp and are refreshed nightly | In place | Y
Owner Parcels | Relevance | Near-term: Datasets are available to partners and the public in any format or filter they require | Develop Open Data Site | Y | 50% - 5/13/2026 | Y (unknown)
Owner Parcels | Relevance | Long-term: Additional resources are made available to help users work with SQL databases more efficiently, reducing the learning curve | Develop material (i.e. better tutorials and videos) | N | 0% | Y
CadNSDI: Townships, Sections, Second Divisions, Special Surveys, Meandering Water | Update Frequency | Current: Annual Publication | In place | Y, reoccuring |  | Y (75 hours / year) |  |  | Involves running a set of scripts and QAQC in order to accomplish this every year
CadNSDI: Townships, Sections, Second Divisions, Special Surveys, Meandering Water | Update Frequency | Long-term: Publish semi-annually, make semi-annual snapshots pubicly available | Streamling QAQC processes | N | 0% | N (150 hours / year) |  |  | Would involve overhauling the QAQC process, not to mention adjusting parcel data multiple times a year. We do not have the staff to accomplish this at this point
CadNSDI: Townships, Sections, Second Divisions, Special Surveys, Meandering Water | Archive Frequency | Current: Annual snapshot, yearly snapshots made publicly available | In place | Y, reoccuring
CadNSDI: Townships, Sections, Second Divisions, Special Surveys, Meandering Water | Archive Frequency | Long-term: Semi-annual snapshots, make a semi-annual snapshot pubicly available | Prioritized more/public need | N |  | N | Y (adding a 0.5 FTE would boost productivity and make more frequent publishing far more feasible) |  | Publishing the CadNSDI more than annually is not currently prioritized, it is difficult to envision more than once being efficient given the time it takes to publish and adjust the assoicated layers
CadNSDI: Townships, Sections, Second Divisions, Special Surveys, Meandering Water | Precision/Accuracy | Current: 1) Varies across state (+/- 160 meters to +/- 0.1 meter) | In place | Y
CadNSDI: Townships, Sections, Second Divisions, Special Surveys, Meandering Water | Precision/Accuracy | Current: Prioritizing funding and resources to adjust MGIA grant projects, then prioritizing current data to adjust the most "in-need" areas | In place | Y
CadNSDI: Townships, Sections, Second Divisions, Special Surveys, Meandering Water | Precision/Accuracy | Near-term: Adjust areas identifed that are most in need of adjustment using survey control from any provider willing to submit data | Develop a evaluation metric to assist with identifying areas of need & create a map of this data clearly showing the "need" areas | N | 0% | Y (30 hours)
CadNSDI: Townships, Sections, Second Divisions, Special Surveys, Meandering Water | Precision/Accuracy | Near-term: Adjust more areas identifed that are most in need of adjustment using survey control from prioritized areas | Justify a need for admistration/legislation to fund the Cadastral Framework more | N | 0% | Y (unknown)
CadNSDI: Townships, Sections, Second Divisions, Special Surveys, Meandering Water | Precision/Accuracy | Long-term: Adjust areas identifed that are most in need of adjustment | Analyze developed data from evaluation metric formula | N | 0% | Y (20 hours)
CadNSDI: Townships, Sections, Second Divisions, Special Surveys, Meandering Water | Precision/Accuracy | Long-term: Leverage more stable or consistent funding to contract the acquistion of control within the areas most "in need" | Justify a need for admistration/legislation to fund the Cadastral Framework more | N | 0% | N (unknown) | Y (either contracting or adding a 0.5 to support the additional incoming control to adjust the CadNSDI)
CadNSDI: Townships, Sections, Second Divisions, Special Surveys, Meandering Water | Consistency | Current: CadNSDI features managed in a parcel fabric | In place | Y, reoccurring
CadNSDI: Townships, Sections, Second Divisions, Special Surveys, Meandering Water | Consistency | Current: BLM and MSL download version not on same time schedule | In place | Y |  |  |  |  | Unfortuately, I do not see one observation improving towards a resolution. BLM HQ prioritizes having a quarterly national update available, regardless if the data was quality data or not, often data exported from production data that has not been fully QC'd.
CadNSDI: Townships, Sections, Second Divisions, Special Surveys, Meandering Water | Consistency | Current: BLM and MSL working within the same enterprise parcel fabric to avoid duplication of work being entered | In place | Y |  |  |  |  | BLM is working in MSL hosted enviornment, it will soon be a service hosted within cloud infrastructure
CadNSDI: Townships, Sections, Second Divisions, Special Surveys, Meandering Water | Consistency | Near-term: Collaborate with BLM to align with their vision for assuming data hosting responsibilities | Coordination with BLM and MSL IT | N | 0% | Y (4 hours)
CadNSDI: Townships, Sections, Second Divisions, Special Surveys, Meandering Water | Consistency | Long-term: Relinquish data hosting responsibilities to BLM while maintaining a key editing contributor role | Coordination with BLM and MSL IT | N | 0% | Y (16 hours)
CadNSDI: Townships, Sections, Second Divisions, Special Surveys, Meandering Water | Completeness | Current: 1) Statewide coverage, on-going maintenance | In place | Y, reoccurring |  | Y (approx. 960 hours / year) {roughly 40% of my time}
CadNSDI: Townships, Sections, Second Divisions, Special Surveys, Meandering Water | Completeness | Current: Missing survey data in some areas or have incorrect parcel line segment/ surveyed line measurements or bearings, due to poor data migration techniques | In place | Y
CadNSDI: Townships, Sections, Second Divisions, Special Surveys, Meandering Water | Completeness | Current: Metadata does not include sufficient feature characteristics or descriptions | In place | Y
CadNSDI: Townships, Sections, Second Divisions, Special Surveys, Meandering Water | Completeness | Near-term: 1) Identify the missing surveys that are missing from into the dataset, 2) Identify incorrect surveyed line measurements or bearing | Analyze missing data | Y | 45% - 4/22/2026 | Y (2 hours)
CadNSDI: Townships, Sections, Second Divisions, Special Surveys, Meandering Water | Completeness | Near-term: Modify metadata to include feature characteristics and descriptions | Incorporate missing information into the metadata | N | 0% | Y (4 hours)
CadNSDI: Townships, Sections, Second Divisions, Special Surveys, Meandering Water | Completeness | Long-term: CadNSDI is complete, with missing surveys & survey lines all incorporated, on-going maintenance | Incorporate missing surveys and survey lines into the fabric | Y | 20% - 4/22/2026 | Y (200 hours)
CadNSDI: Townships, Sections, Second Divisions, Special Surveys, Meandering Water | Timeliness | Current: Aquire control & CRR derived control from a MGIA funded project often has a lag of when the new adjusted data is incorporated into the CadNSDI by 1-2 years | In place | Y
CadNSDI: Townships, Sections, Second Divisions, Special Surveys, Meandering Water | Timeliness | Current: Several dozen of surveys either have missing from the parcel fabric or have missing Entered parcel lines, which reconciling all of the missing components slows down the adjustment process | In place | Y
CadNSDI: Townships, Sections, Second Divisions, Special Surveys, Meandering Water | Timeliness | Long-term: Improve the lag difference of when aquired control from MGIA funded projects | Streamlining/improving the adjustment process | Y | 15% | Y (unknown)
CadNSDI: Townships, Sections, Second Divisions, Special Surveys, Meandering Water | Integrity | Current: CadNSDI attribute validation concerns statewide | In place | Y
CadNSDI: Townships, Sections, Second Divisions, Special Surveys, Meandering Water | Integrity | Current: New survey control is acquired from either MGIA PLSS grant projects or what is submitted to the Mapping Control Theme Lead (from mostly data partners, occasionally private surveyors) | In place | Y, reoccurring
CadNSDI: Townships, Sections, Second Divisions, Special Surveys, Meandering Water | Integrity | Near-term: Identify control acquistion targets within identified areas in need of an adjustment | Develop a evaluation metric to assist with identifying areas of need | N | 0% | Y | Y (with 25-30% of a Technician total time)
CadNSDI: Townships, Sections, Second Divisions, Special Surveys, Meandering Water | Integrity | Near-term: Evaluate attribute validation concerns and prioritize areas most in need of being validated | Analyze the data and create updated validaton priority areas | N | 33% - 5/1/2026 | Y (4 hours) |  |  | This process we do every year, but the criteria for prioritization changes based on either MSL or BLM needs or upcoming adjustment workplan or funding direction for BLM HQ
CadNSDI: Townships, Sections, Second Divisions, Special Surveys, Meandering Water | Integrity | Long-term: Acquire 35% of every "surveyed" township corner of the state, every section and/or quarter corner surrounding populated towns by 2036 | Target specific counties or DOR to apply for MGIA grant funds | N | 0% | Y (with 25-30% of a Technician total time) |  | $2500 (in additional training and time) | An additional 45-50 desired control would be incoming each year, which would still create a strain on current resources, an additional ask of Techs time or contract to work out
CadNSDI: Townships, Sections, Second Divisions, Special Surveys, Meandering Water | Relevance | Current: Datasets are available to partners and the public in several formats | In place | Y
CadNSDI: Townships, Sections, Second Divisions, Special Surveys, Meandering Water | Relevance | Near-term: Datasets are available to partners and the public in any format or filter they require | Develop Open Data Site | Y | 50% - 5/13/2026 | Y (unknown)
Conservation Easements | Update Frequency | Current: Publish monthly, based on when data is submitted by DOR | In place | Y
Conservation Easements | Archive Frequency | Current: Monthly archives, yearly snapshots made publicly available |  | Y, reoccurring
Conservation Easements | Archive Frequency | Long-term: Make a semi-annual snapshots pubicly available |  | N | 0% | Y |  |  | Not prioritized at the moment
Conservation Easements | Precision/Accuracy | Current: Varies across state (+/- 160 meters to +/- 0.1 meter); Most are mapped to current CadNSDI | In place
Conservation Easements | Precision/Accuracy | Near-term: Adjust areas identifed that are most in need of adjustment (survey control or re-COGO | Identify areas in-need the most of an adjustment by creating a map that is updated annually and clearly shows the "need" areas | N |  | Y
Conservation Easements | Precision/Accuracy | Long-term: Adjust areas identifed that are most in need of adjustment (survey control or re-COGO | Continue to adjust adjustment areas "in-need" the most and prioritize "existing" funding and resources accordingly | N | 0% | Y
Conservation Easements | Precision/Accuracy | Long-term: Adjust areas identifed that are most in need of adjustment (survey control or re-COGO | Continue to adjust adjustment areas "in-need" the most and prioritize any funding and resources accordingly | N | 0% | N (this objective takes in account additional funding to acquire control more "in-need" areas, in additional to control being acquired using MGIA funding through the grant program
Conservation Easements | Consistency | Current: Adjusted to the latest CadNSDI | In place | Y, reoccurring |  | Y (6 hours / year)
Conservation Easements | Consistency | Current: Not managed in a parcel fabric with the ownerparcels | In place | Y
Conservation Easements | Consistency | Current: 1) Easements can occasionally get missed that were recorded at the county information is passed along to DOR, 2) The Easement data currently doesn't include any information about amendments and condemnations | In place | Y |  | Y
Conservation Easements | Consistency | Near-term: 1) Investigate ways to make improvements to the Easement routing process, 2) Investigate whether including additional information about the easement | Coordination with DOR | N | 0% | Y
Conservation Easements | Consistency | Long-term: Production data in the same parcel fabric as the OwnerParcels | Coordination with DOR | N | 0% | Y
Conservation Easements | Consistency | Long-term: 1) Improvements made to routing process to ensure new Easements are entered into the GIS data in a more timely manner, 2) Additional fields and data are incorporated into the Easements | Coordination with DOR | N | 0% | Y
Conservation Easements | Completeness | Current: Statewide coverage, on-going maintenance | In place | Y, reoccurring |  | Y |  |  | DOR maintains the geometry and GIS attribute for the Conservation Easements
Conservation Easements | Timeliness | Current: Easement data lag from the time the easement is recorded to when it is entered into the service | In place | Y
Conservation Easements | Timeliness | Long-term: An improved lag difference when changes are incorporated into the Conservation Easements GIS service | Coordinate with DOR & county offices | N
Conservation Easements | Integrity | Current: Easements can get out of alignment with parcel data which may not be caught for several months, a concern to address in the future | In place | Y |  | Y
Conservation Easements | Integrity | Current: Submission data feature class schema does not match the data schema that the public downloads/views | In place | Y |  | Y
Conservation Easements | Integrity | Near-term: Coordinate with the parcel editors to implement an improved process to help ensure the timing of the misalignments are minimized | Coordination with all parcel providers | N | 0% | Y
Conservation Easements | Integrity | Near-term: data provider's schema matches the published Conservation Easements schema | Coordination with DOR | Y | 100% - 3/15/2026 | Y
Conservation Easements | Integrity | Long-term: Conservation Easements and Owner Parcels are aligned with one another | Coordination with all parcel providers | N | 0% | Y
Conservation Easements | Relevance | Current: Easement data not completely up-to-date, making the service unreliable | In place | Y |  | Y
Conservation Easements | Relevance | Current: Datasets are available to partners and the public in several formats | In place | Y |  | Y
Conservation Easements | Relevance | Near-term: Datasets are available to partners and the public in any format or filter they require | Develop Open Data Site | Y | 50% - 5/13/2026 | Y (unknown)
Public Lands | Update Frequency | Current: Quarterly updates, occasionally updated after large public acquisition | In place | Y, reoccurring |  | Y
Public Lands | Update Frequency | Long-term: Update and publish monthly | Prioritized more | N, reoccurring |  | Y (with help from a Technician) |  |  | Not prioritized at the moment to edit the Public Lands dataset more than what is currently implemented, workload help from a Technician would go a long way of updating the dataset more frequently
Public Lands | Archive Frequency | Current: Quarterly archives, yearly snapshots made publicly available | In place | Y, reoccurring |  | Y
Public Lands | Archive Frequency | Long-term: Make a semi-annual snapshots pubicly available | Prioritized more | N, reoccurring |  | Y (with help from a Technician)
Public Lands | Precision/Accuracy | Current: Varies across state (+/- 160 meters to +/- 0.1 meter); Most are mapped to current CadNSDI | In place | Y |  | Y
Public Lands | Precision/Accuracy | Near-term: Adjust areas identifed that are most in need of adjustment (survey control or re-COGO); prioritize available funding and resources | Identify areas in-need the most of an adjustment by creating a map that is updated annually and clearly shows the "need" areas | N | 0% | Y
Public Lands | Precision/Accuracy | Long-term: Adjust areas identifed that are most in need of adjustment (survey control or re-COGO); prioritize available funding and resources | Continue to adjust adjustment areas "in-need" the most and prioritize any funding and resources accordingly | N | 0% | Y
Public Lands | Consistency | Current: Adjusted to the latest CadNSDI | In place | Y, reoccurring |  | Y (10 hours / year)
Public Lands | Consistency | Current: Missing public lands that appear in DOR's owner information but the change was not reflected in the public lands | In place | Y |  | Y
Public Lands | Consistency | Near-term: Perform a comprehensive review of each dataset and highlight discrepancies between each dataset | Prioritized more | N, reoccurring |  | Y (16 hours, with help from a Technician) |  |  | This objective has not been accomplished since 2023 and is not apart of annual priorities
Public Lands | Consistency | Near-term: Develop process to better detect ownership changes that impact public lands | Better reporting and analysis is needed to detect ownership changes that impacts public lands | N |  | Y (16 hours, with help from a Technician) |  |  | This type of reporting is difficult to completely flush out, DOR doesn't prioritize exempt property changes and discrepancies that are discovered by partners are very slow to change if at all. Public land edits tend to stack up over a 3 month period and some changes are false positives as some counties take OwnerParcel of a property if taxes are failed to be over a significant period, then the property is sold in an auction meaning the property was never aquired with public management intention
Public Lands | Consistency | Long-term: Coordinate with DOR and each data provider to reconcile management/owner attribution differences between datasets | Coordinate with all data providers | N, reoccurring |  | Y (unknown, with help from a Technician) |  |  | This objective is not currently prioritized
Public Lands | Consistency | Long-term: Public Land ownership matches Owner Name in OwnerParcel | Better reporting and analysis is needed to detect ownership changes that impacts public lands | N |  | Y (with help from a Technician)
Public Lands | Completeness | Current: Statewide coverage, on-going maintenance | In place | Y, reoccurring |  | Y (35 hours / year) |  |  | Only providing updates on a quarterly basis or if there is a major acquisition, land swap or sale involving state trust land
Public Lands | Timeliness | Current: Public Land ownership lag from the time the change appears in the CAMA to when it'll appear in the GIS service | In place | Y |  | Y
Public Lands | Timeliness | Long-term: An improved lag difference when changes are incorporated into the Public Lands GIS service | Prioritized more/public need | N |  | Y (40 hours, with help from a Technician)
Public Lands | Integrity | Current: Public Lands are not completely seamless, often following the parcel boundaries that have the same issues within its' data | In place | Y |  | Y
Public Lands | Integrity | Current: Public Lands can get out of alignment with parcel data which may not be caught for several months, a concern to address in the future | In place | Y |  | Y
Public Lands | Integrity | Near-term: Implement topology check to detect overlaps and gaps | Implement better topology checks practice | N | 0% | Y (3 hours) |  |  | I would anticipate 20 hours a year spent on this once the current issues are resolved but for now, I would estimate 60 hours
Public Lands | Integrity | Near-term: Implement an improved process to help ensure the timing of the misalignments are minimized | Coordination with parcel providers | N | 0% | Y (25 hours)
Public Lands | Integrity | Long-term: Public Lands dataset contains no unintended gaps / overlaps | Implement better topology checks practice | N |  | Y (with help from a Technician) |  |  | This objective is difficult to prioritize in the near future but as input data quality improves, so will making it easier to implement significant actions onto a large dataset
Public Lands | Integrity | Long-term: Public Lands and Owner Parcels are aligned with one another | Coordination with parcel providers & is critical to resolve parcel seamless issue in parallel | N |  | Y (with help from a Technician) |  |  | This objective is difficult to prioritize in the near future as there are more prevelant issues at hand
Public Lands | Relevance | Current: Inconsistencies between Owner info in parcels vs public lands vs agency datasets can lead to confusion, or may make data unreliable for certain uses | In place | Y |  | Y
Public Lands | Relevance | Current: Unintended gaps & overlaps exist in the public lands data, causing confusion for the users of this service/indirectly within an application | In place | Y |  | Y
Public Lands | Relevance | Long-term: Improve public lands owner info inconsistencies | Coordination with all data providers to resolve major owner discrepancies | N |  | Y (with help from a Technician) |  |  | This type of reporting is difficult to completely flush out, other data partner's data tend to conflict with DOR's and the time to research or search for evidence is not currently a priority for MSL
Public Lands | Relevance | Long-term: Resolve all unintended gaps & overlaps in order to improve the data's reliability | Implement better topology checks practice | N |  | Y (with help from a Technician) |  |  | This objective will need the vast majority of the work performed by a Technician. It is difficult to fully put a resolution to this objective as the quality of the public lands relies heavily on the quality of the OwnerParcels that MSL doesn't maintain. In theory as input data quality improves, so will the public lands data, which will make it easier to implement significant actions onto a large dataset
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
Note on C97: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: “Update and publish monthly”? Reply: Corrected

## Value List
Measure | Definition
select from list
Update Frequency | Update Frequency: This is an aspect of "Timeliness", specified in this assessment because it is usually an explicit part of data management workflows
Archive Frequency | Archive Frequency: This is an aspect of "Timeliness", specified in this assessment because it is usually an explicit part of data management workflows
Precision/Accuracy | Precision/Accuracy: A measure of the accuracy of the data. Is the accuracy stated? Does it match end user’s needs?
Consistency | Consistency: A measure of the similarities and differences between data stored in multiple datasets or databases.
Completeness | Completeness: A measure of how comprehensive the information in a dataset is. Are required or priority fields populated?
Timeliness | Timeliness: An assessment of the data’s update cycles, and temporality to internal and external deadlines and reporting needs.
Integrity | Integrity: An assessment of whether the data’s structure, schema and maintenance workflows meet end user’s needs and support interopability between systems
Relevance | Relevance: An assessment of the accessibility and availability of data required to inform business systems and answer business questions.